## Sheet1
	Project Name : Bug Tracking System

1	Scrum – sprint -1(project Baseline)
2	Database wireframe preparation	04-05-2019
3	Database Script preparation	06-05-2019
4	Database Review/execution	07-05-2019
5	Abstraction Document Preparation	07-05-2019
6	Project – Baseline setup	07-05-2019
7	Project – maven integration with dependencies	07-05-2019
8	Project – Identify the business objects	07-05-2019
9	Project – display menu items	07-05-2019
10	Adding – Common Modules (Login module, Payment module, Utilities)	08-05-2019
11	Project – Validation Implementation (UI Layer)	08-05-2019
12	Project – DAO Implementation (DAO Layer)	08-05-2019
13	Servlet/Controller Implementation	09-05-2019
14	Service/Business Implementation	09-05-2019
15	Feature wise – DAO Implementation	10-05-2019
16	Utilities – Common Functionality Implementation	10-05-2019
17	JavaScript Session part 1	14-05-2019
18	Project Updates, Agile Introduction	14-05-2019
19	Project Demo	14-05-2019
20	one to one Discussions	14-05-2019
21	SQL Batch Update- Sample	15-05-2019
22	Junit Session	15-05-2019
23	Log4j session	15-05-2019
24	Utilities – External Utility API (String Utils, File Utils)	16-05-2019
25	Convert Dynamic web -> Maven Project	16-05-2019
26	JavaScript (Page redirect, Dialog boxes, HTML DOM, Validations) (Part-2)	17-05-2019
27	One to one Questions	17-05-2019
28	Project Demo – 2nd Review	17-05-2019
29	Assessment- L2 & L3	17-05-2019
30	Scenario based Questions (discussion)	17-05-2019
31	Jquery/Js Ajax (diff)	20-05-2019
32	JDBC/GC/Arrays	20-05-2019
33	Web Application Configuration	20-05-2019
34	Abstract Document – reviewed	21-05-2019
35	Demo – Project Review(3rd )	21-05-2019
36	Naming Convention/ Coding Standards	21-05-2019
37	Defined exception / joins/sub query	21-05-2019
38	UI – Validation/ alignments/css	21-05-2019
39	Final Project Review
40	Demo to client
41	Share Source code / DB script (Git Repository)